## EXAMPLE Agile Project Timeline
Agile Project Timeline Template Example
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Product Release |  |  | Alex B. |  | 2028-01-16 | 2028-04-21 | 35% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 |  | Alex B. |  | 2028-01-16 | 2028-02-15 | 31
Yes | Feature 1 |  | Frank C. |  | 2028-01-16 | 2028-02-02 | 18 | Complete | High
No | Feature 2 |  | Jacob S. |  | 2028-01-31 | 2028-02-05 | 6 | In Progress | Medium
| Feature 3 |  | Jacob S. |  | 2028-02-05 | 2028-02-15 | 11 | Not Started | Low
| SPRINT 2 |  | Jacob S. |  | 2028-01-22 | 2028-02-25 | 35
| Feature 1 |  | Alex B. |  | 2028-01-22 | 2028-01-29 | 8 | Overdue
| Feature 2 |  | Frank C. |  | 2028-01-28 | 2028-01-31 | 4 | Needs Review
| Feature 3 |  | Shari W. |  | 2028-01-29 | 2028-02-25 | 28 | Approved
| SPRINT 3 |  | Shari W. |  | 2028-02-28 | 2028-03-16 | 18
| Feature 1 |  | Alex B. |  | 2028-02-28 | 2028-03-01 | 3 | On Hold
| Feature 2 |  | Kennedy K. |  | 2028-02-28 | 2028-03-04 | 6
| Feature 3 |  | Jacob S. |  | 2028-03-01 | 2028-03-16 | 16
| SPRINT 4 |  | Jacob S. |  | 2028-03-16 | 2028-04-16 | 32
| Feature 1 |  | Jacob S. |  | 2028-03-16 | 2028-03-17 | 2
| Feature 2 |  | Jacob S. |  | 2028-03-18 | 2028-03-20 | 3
| Feature 3 |  | Alex B. |  | 2028-03-24 | 2028-04-16 | 24
| SPRINT 5 |  | Frank C. |  | 2028-03-24 | 2028-04-21 | 29
| Feature 1 |  | Shari W. |  | 2028-03-24 | 2028-03-26 | 3
| Feature 2 |  | Shari W. |  | 2028-03-26 | 2028-04-05 | 11
| Feature 3 |  | Kennedy K. |  | 2028-04-06 | 2028-04-21 | 16
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Agile Project Timeline
Agile Project Timeline Template
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
[7 empty] | 0% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
SPRINT 1
Feature 1
Feature 2
Feature 3
SPRINT 2
Feature 1
Feature 2
Feature 3
SPRINT 3
Feature 1
Feature 2
Feature 3
SPRINT 4
Feature 1
Feature 2
Feature 3
SPRINT 5
Feature 1
Feature 2
Feature 3
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.