## EXAMPLE - Event Risk Management
Event Risk Management Template Example
Event Name | [5 empty] | Risk Summary
Event Date |  |  |  |  | Mitigated Risks |  | 1
Venue / Location |  |  |  |  | Open / Monitoring Risks |  | 1
Event Organizer / Contact |  |  |  |  | High-Impact Risks |  | 3
Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Responsible Party | Status | Last Updated | Notes
Weather
R-001 | Rain during outdoor event | High | High | Rent tents; have indoor backup | Logistics Lead | Mitigated | 2025-09-01 | Confirm tent delivery.
Staffing
R-002 | Key speaker cancellation | Medium | High | Have alternate on standby | Program Coordinator | Monitoring | 2025-09-02 | Speaker flight confirmed.
Technology
R-003 | A/V system failure | Low | Medium | Pre-event equipment test | AV Manager | In Progress | 2025-09-03 | Include backup microphones.
Health & Safety
R-004 | COVID-19 exposure risk | Medium | High | Provide masks; increase ventilation | Safety Officer | Planned | 2025-09-01 | Provide hand sanitizer stations too.
Other Risks
Risk Assessment Completed By | Signature |  |  | Date
Risk Assessment Approved By | Signature |  |  | Date
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Event Risk Management
Event Risk Management Template
Event Name | [5 empty] | Risk Summary
Event Date |  |  |  |  | Mitigated Risks |  | 0
Venue / Location |  |  |  |  | Open / Monitoring Risks |  | 0
Event Organizer / Contact |  |  |  |  | High-Impact Risks |  | 0
Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Responsible Party | Status | Last Updated | Notes
Weather
Staffing
Technology
Health & Safety
Other Risks
Risk Assessment Completed By | Signature |  |  | Date
Risk Assessment Approved By | Signature |  |  | Date

## Drop Down Lists
Drop Down Lists Do Not Delete
Likelihood | Impact | Status
Low | Low | Mitigated
Medium | Medium | Monitoring
High | High | In Progress
Planned

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.