## 1. Film Budget DASHBOARD
Feature Film Budget Template Example
Film Title | This Side of Midnight |  |  |  |  | "This Side of Midnight"
Producer(s) | Alexandra Mattson and Aviv Perez
Production Company | Sidecar Films
Budget Version | V 1.0 - Initial Lock
Date Prepared | MM/DD/YY
Currency | USD
At-A-Glance
KPI Data (shaded cells auto-populate)
Total % of Budget Used | 89.03%
Budget Remaining (Actual - Projected) | -64492
Number of Tabs Completed | 4
Last Updated | MM/DD/YY
Users are to complete the accompanying Tabs 2 through 13. Shaded cells in the Dashboard Tables below pull content directly from these tabs. The charts above will be auto-populated by the Dashboard Tables below.
Category Totals
Budget Category | Projected Totals | Actual Total | Variance | Status | Overage Notes and Explanation (does not auto-populate)
Above-The-Line | 200000 | 202000 | 2000 | Over
Production (Below-the-Line) | 160000 | 156979 | -3021 | OK
Post-Production (Below-the-Line) | 85000 | 70489 | -14511 | OK
Marketing and Publicity | 48000 | 49500 | 1500 | Over
Legal, Accounting, and Admin | 45000 | 44540 | -460 | OK
Contingency | 50000 |  | -50000 | OK | Included
Total Feature Film Budget | 588000 | 523508 | -64492 | OK
Budget Category | Projected Totals by %
Above-The-Line | 38.2%
Production (Below-the-Line) | 30.56%
Post-Production (Below-the-Line) | 16.24%
Marketing and Publicity | 9.169%
Legal, Accounting, and Admin | 8.596%
Contingency | 9.551%
CLICK HERE TO CREATE IN SMARTSHEET

## 2. Above-The-Line BUDGET
Budget Category: Above-The-Line
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Line Item | Quantity | Rate | Line Total | Notes
Producer(s) | 1 | 30000 | 30000 | Flat fee
Executive Producer(s) | 2 | 15000 | 30000 | Total for both
Director | 1 | 40000 | 40000 | 5 weeks plus prep
Writer(s) | 2 | 12500 | 25000 | Split among two writers
Lead Actor(s) | 2 | 25000 | 50000 | Star / lead talent
Supporting Actor(s) | 5 | 2000 | 10000 | Day players and minor roles
Casting Director | 1 | 5000 | 5000 | Three-week engagement
Rights Acquisition | 1 | 5000 | 5000 | Short-story license
Development Costs |  | 2500 | 2500 | Script coverage, research
Legal Fees (ATL) |  | 2500 | 2500 | Deal memos, contracts
Travel / Meetings |  | 2000 | 2000 | Director / prod meetings
Line Item |  | 0 | 0
Line Item |  | 0 | 0
Line Item |  | 0 | 0
Line Item |  | 0 | 0
Subtotal |  |  | 202000
Projected Total |  |  | 200000

## 3. Production BUDGET
Budget Category: Production
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Department | Line Item | Quantity | Rate (per day) | Total Days | Line Total | Notes
Camera | DP | 1 | 357 | 21 | 7497 | Three weeks
Lighting and Grip | Gaffer, Best Boy, Grip | 3 | 214 | 21 | 13482 | Three weeks
Sound | Mixer, Boom Operations | 2 | 200 | 21 | 8400 | Three weeks
Production Design | Designer and Team |  | 25000 |  | 25000
Wardrobe | Costumes, Stylists |  | 8000 |  | 8000
Locations | Permits, Fees |  | 6000 |  | 6000
Transport | Trucks, Vans |  | 9000 |  | 9000
Catering and Craft |  | 20 | 20 | 18 | 7200
Insurance | Production |  | 20000 |  | 20000 | General and equipment
Set Construction | Flats, Build, Paint |  | 18000 |  | 18000
Contingency | 10% |  | 34400 |  | 34400 | Built into total
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Subtotal |  |  |  |  | 156979
Projected Total |  |  |  |  | 160000

## 4. Post-Production BUDGET
Budget Category: Post-Production
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Line Item | Quantity | Rate (per day) | Total Days | Line Total | Notes
Editor | 1 | 357 | 35 | 12495 | Five weeks
Color Correction |  | 6000 |  | 6000 | Final conform and grading
Composer |  | 7500 |  | 7500 | Score
Sound Mix |  | 5000 |  | 5000 | 5.1 plus stereo
ADR / Foley |  | 4500 |  | 4500 | On site
Titles and Graphics |  | 2500 |  | 2500 | Lower thirds, credits
Post Supervision | 1 | 214 | 21 | 4494
Mastering / Output |  | 3000 |  | 3000 | DCP, ProRes, Backups
VFX |  | 15000 |  | 15000 | Six shots
Music Licensing |  | 10000 |  | 10000 | Four pre-cleared tracks
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
Subtotal |  |  |  | 70489
Projected Total |  |  |  | 85000

## 5. Marketing & Publicity BUDGET
Budget Category: Marketing & Publicity
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Line Item | Quantity | Rate (per day) | Line Total | Notes
Trailer Production | 1 | 8000 | 8000 | Includes teaser
Poster Design and Print |  | 4000 | 4000 | 300 units
PR Firm Retainer | 2 | 7500 | 15000 | Pre-release and launch
Press Kits |  | 1500 | 1500 | PDF and print
Social Media Campaign |  | 5000 | 5000 | Boosted posts
Influencer Marketing |  | 6000 | 6000 | Four partnerships
Festival Promotion |  | 10000 | 10000 | TIFF, SXSW outreach
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Subtotal |  |  | 49500
Projected Total |  |  | 48000

## 6. Legal, Acct, Admin BUDGET
Budget Category: Legal, Accounting and Administrative
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Line Item | Quantity | Rate (per day) | Total Days | Line Total | Notes
Legal (Production) |  | 10000 |  | 10000 | Contracts, rights, NDAs
Production Accounting | 1 | 66 | 90 | 5940 | Three months
Permit Fees |  | 3000 |  | 3000 | City, drone, night shoot
Insurance (E&O) |  | 8000 |  | 8000 | Errors and omissions policy
Office Supplies |  | 1000 |  | 1000 | Printer, paper, toner, drives
Software Licenses |  | 2000 |  | 2000 | Zoom, Slack, Studio Binder
Administrative Staff | 2 | 80 | 60 | 9600 | Two months, production coordinator and office PA
Contingency (Admin) |  | 5000 |  | 5000 | Buffer for extension, surprises
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
Subtotal |  |  |  | 44540
Subtotal |  |  |  | 45000

## 7. Dist. and Delivery BUDGET
Budget Category: Distribution and Delivery
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Line Item | Quantity | Rate (per day) | Line Total | Notes
DCP Creation | 2 | 2000 | 4000 | Theatrical and backup
Closed Captioning | 1 | 1000 | 1000 | For English CC
Subtitles - Spanish | 1 | 2000 | 2000 | Festival and streaming delivery
Platform Aggregator | 1 | 5000 | 5000 | Streaming services
Delivery drives, Archive |  | 3000 | 3000 | LTO backup, cloud, RAID
Metadata / Artwork Prep |  | 1500 | 1500 | Platform assets (poster, synopsis)
Festival Submission Fees | 15 | 60 | 900 | Post-premiere rounds
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Subtotal |  |  | 17400
Projected Total |  |  | 17000

## 8. Cash Flow TRACKER
Cash Flow Tracker
Tab 1's Dashboard will pull data from this table. Shaded cells in the table below will auto-populate.
Phases | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | Total Outflow (Actual Spend)
| Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark | Projected Spend | Actual Spend | Benchmark
Pre-Production | [36 empty] | 0
ATL | 10000 | 9000 | 9000 | 10000 | 9000 | 9000 | 10000 | [29 empty] | 18000
Prod | 7500 | 7500 |  | 7500 | 7500 | [31 empty] | 15000
Admin | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | [30 empty] | 2400
0
0
0
Production Week 1 | [36 empty] | 0
Marketing | [6 empty] | 10000 | [29 empty] | 0
Admin | [6 empty] | 1200 | 1200 | 1200 | [27 empty] | 1200
ATL | [6 empty] | 5000 | 5000 | 4500 | [27 empty] | 5000
0
0
0
Production Week 2 | [36 empty] | 0
Prod | [6 empty] | 10000 | [29 empty] | 0
Admin | [6 empty] | 1200 | 1200 | 1200 | [27 empty] | 1200
0
0
0
0
Production Week 3 | [36 empty] | 0
Post | [9 empty] | 30000 | 35000 | 32000 | [24 empty] | 35000
Marketing | [9 empty] | 15000 | 12000 | 14000 | [24 empty] | 12000
Admin | [9 empty] | 1200 | 1200 | 1200 | [24 empty] | 1200
0
0
0
Post Production Month 1 | [12 empty] | 125000 | 115000 | [22 empty] | 115000
Delivery | [36 empty] | 0
Marketing | [36 empty] | 0
0
0
0
0
Post production Month 2 | [36 empty] | 0
Delivery | [36 empty] | 0
Marketing | [36 empty] | 0
0
0
0
Monthly Totals | 18700 | 17700 | 10200 | 18700 | 17700 | 10200 | 37400 | 7400 | 6900 | 46200 | 48200 | 47200 | 125000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206000
Data for Dashboard Chart (this pulls from above table - do not delete)
Monthly Totals
| Projected | Actual | Benchmark
January | 18700 | 17700 | 10200
February | 18700 | 17700 | 10200
March | 37400 | 7400 | 6900
April | 46200 | 48200 | 47200
May | 125000 | 115000 | 0
June | 0 | 0 | 0
July | 0 | 0 | 0
August | 0 | 0 | 0
September | 0 | 0 | 0
October | 0 | 0 | 0
November | 0 | 0 | 0
December | 0 | 0 | 0

## 9. Notes and Assumptions
Notes and Assumptions
Line Item / Area | Notes
Lead Actor Fee | Includes agency commission; 3-week shoot, 1-week prep
Location Fees | Includes security, overtime agreements
Contingency | Set at 10% of Production + Admin
PR Retainer | Locked at $7,500/month × 2 months
Composer | Flat fee buyout – no back-end royalties
Aggregator Fee | Includes 4 platforms + QC pass
In-kind Donations | Valued conservatively, not tax-deductible
Music Licensing | 2 indie tracks at $2,500 + 2 library cues at $2,500

## 10. Funding Sources
Funding Sources
Shaded cells in the table below will auto-populate.
Funding Sources | Amount Committed | Amount Received | Date Received | Type | Notes
Private Equity - A | 200000 | 200000 | MM/DD/YY | Private Equity | Closed round
Private Equity - B | 15000 | 75000 | MM/DD/YY | Private Equity | 50% on delivery
Kickstarter | 60000 | 60000 | MM/DD/YY | Crowdfunding | After fees: $56,400
State Film Grant (Oregon) | 120000 | 0 | MM/DD/YY | Pending Gov. Grant | Will apply post-production
Tax Credit Estimate | 90000 | 0 | MM/DD/YY | Incentive | Estimate only
Brand Sponsorship | 20000 | 20000 | MM/DD/YY | In-kind and cash | Product placement
Producer Contribution | 10000 | 10000 | MM/DD/YY | Personal | Seed money
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
| 0 | 0 | MM/DD/YY
Total Funding | 515000 | 365000

## 11. Payroll Summary
Payroll Summary
Shaded cells in the table below will auto-populate.
Department | Position | Name | Union | Rate | Rate Type | Days/Weeks/Months | Total Pay | Notes
Cast | Lead Actor 1 | R. Delgado | Y | 10000 | Weekly | 3 | 30000 | SAG Schedule F
Production | DP | M. Yu | Y | 2500 | Weekly | 3 | 7500 | IATSE
Art Department | Set Decorator | T. Bianchi | N | 350 | Daily | 18 | 6300 | Non-Union
Post | Editor | A. Kim | y | 2500 | Weekly | 5 | 12500
Admin | Production Coordinator | J. Han | N | 2500 | Monthly | 1 | 2500
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
Total Payroll | [6 empty] | 58800

## 12. In-Kind Donations
In-Kind Donations
Shaded cells in the table below will auto-populate.
Item / Service Donated | Donor | FMV | Use in Production | Confirmed | Notes
Office Space (1 month) | Realty Co. | 2500 | Production Office | Y | Lobby space, basic furnishings
Equipment - Grip Truck | Grip FX Rentals | 4000 | G&E | Y | Full three-week use
Catering (1 week) | Local Kitchen | 1800 | Crew Meals | Y | Vegan-friendly sponsor
Wardrobe Loan | Vintage Vault | 1200 | Costume Department | Y | 1950s vintage items
0
0
0
0
0
0
0
0
0
0
0
| Total In-Kind Value | 9500

## 13. Int. and Local Incentives
International and Local Incentives
Shaded cells in the table below will auto-populate.
Incentive Program | Location | Type | Eligible Spend | Rebate % | Est. Rebate | Status | Notes
Oregon Production Rebate | Oregon, USA | Cash Rebate | 400000 | 25% | 100000 | Will apply | Regional and labor included
Canadian Post Prod Office | Toronto, Canada | Tax Credit | 100000 | 16% | 16000 | Not applied | Need CDN post house
UK Film Tax Relief | UK | Tax Credit | 200000 | 20% | 40000 | Approved | Cultural test passed
Georgia Film Credit | Georgia, USA | Transferable | 100000 | 30% | 30000 | Pre-Approved | Requires peach logo on screen
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
|  |  | 0 | 0% | 0
Total Incentives |  |  |  |  | 186000

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.