## EXAMPLE - Budget Proposal
Project Budget Proposal Template – Example
Project Budget Proposal
Project Title
Solar-Powered Water Purification System for Rural Communities
Project Manager
Dr. Guadalupe Garcia
Department / Organization |  |  |  | Submission Date
Environmental Engineering & Technology |  |  |  | February 15, 20XX
Prepared by |  | Reviewed by |  | Approved by
Dr. Guadalupe Garcia |  | Krista Ahmed |  | Victoria Pearson
Project Overview & Objectives
Project Description
Briefly describe the project's purpose, scope, and key deliverables.
This project focuses on the design and implementation of solar-powered water purification systems in rural communities across Sub-Saharan Africa. The goal is to provide clean and safe drinking water to underserved populations using sustainable energy sources. The project will involve developing and installing 50 solar-powered water purification units, training local personnel for maintenance, and monitoring the impact on public health over three years.
Objectives
Objective 1 | Install 50 solar-powered water purification units in 25 rural communities by the end of 20XX.
Objective 2 | Train 100 local community members on system maintenance and water safety.
Objective 3 | Reduce waterborne diseases by 30% in the target regions within three years.
Budget Summary
Total Budget
1800000
Expense Breakdown
Personnel Costs |  | 1050000
Operating Costs |  | 150000
Capital Expenditures |  | 450000
Contingency Fund |  | 150000
Budget Proposal Justification
Justification
Explain why the requested budget is necessary to achieve the project’s objectives. Provide detailed reasoning for key expenses, including personnel, equipment, or capital investments. Highlight how each budget category contributes to the successful completion of the project and aligns with organizational goals or strategic initiatives.
The requested budget is critical to completing this project. Personnel costs are necessary for hiring engineers, trainers, and project managers to oversee the installation's technical and operational aspects. Operating costs cover travel to rural areas, training local staff, and post-installation maintenance support. Most of the budget is allocated to capital expenditures to purchase and install solar-powered water purification units.
Key Investments
Personnel |  | Hiring of engineers, trainers, and local technicians
Technology |  | Solar-powered water purification units and monitoring systems
Training |  | On-site training for community members to maintain the systems
Anticipated Revenue
Revenue Source |  |  |  | Amount ($)
Government Grants |  |  |  | 700000
Corporate Sponsorships |  |  |  | 300000
Donations |  |  |  | 150000
Sales Revenue (training materials) |  |  |  | 100000
Other (specify)
Total Projected Revenue |  |  |  | 1250000
Funding Sources
Funding Source |  |  |  | Amount ($)
Internal Funding |  |  |  | 500000
External Grants / Sponsorships |  |  |  | 750000
Other |  |  |  | 750000
Total Projected Funding |  |  |  | 2000000
Direct Costs
Personnel Costs
Category |  | Description |  | Amount ($)
Project Manager Salary |  | Project implementation oversight |  | 100000
Engineers (4) |  | Technical design and implementation expertise |  | 160000
Local Technicians |  | System maintenance |  | 90000
Other (specify)
Total Personnel Costs |  |  |  | 350000
Materials & Supplies
Category |  | Description |  | Amount ($)
Solar Panels & Hardware |  | Power for purification units |  | 250000
Purification System Materials |  | Filters, sensors, water storage |  | 200000
Other (specify)
Total Materials & Supplies |  |  |  | 450000
Subcontractors
Category |  | Description |  | Amount ($)
Installation Contractors |  | Installation services for 50 units |  | 200000
Training Contractors |  | On-site training of local staff |  | 50000
Other (specify)
Total Subcontractors |  |  |  | 250000
Total Direct Costs |  |  |  | 1050000
Indirect Costs (Overhead)
Category |  | Description |  | Amount ($)
Overhead Costs |  | Rent, utilities, and administrative support |  | 100000
Administrative Costs |  | Legal, finance, and HR services |  | 50000
Other (specify)
Total Indirect Costs |  |  |  | 150000
Capital Expenditures
Category |  | Description |  | Amount ($)
Equipment Purchases |  | Solar-powered purification units |  | 400000
Infrastructure Upgrades |  | Facility expansion for storage |  | 50000
Other (specify)
Total Capital Expenditures |  |  |  | 450000
Contingency & Risk Management
Contingency Fund
150000
Justification for Contingency
Explain why a contingency fund is necessary for this project, such as accounting for unexpected costs, delays, or changes in project scope.
The contingency fund covers unforeseen costs such as delays in equipment delivery, increased material costs, or additional technical support.
Risk Assessment
Risks |  |  | Mitigation Strategies
Delays in procurement and delivery of solar equipment |  |  | Secure multiple vendors and initiate early procurement.
Insufficient training of local technicians leading to system malfunctions |  |  | Include follow-up training and support visits for local technicians.
Cost Summary
Category |  |  |  | Total ($)
Total Direct Costs |  |  |  | 1050000
Total Indirect Costs |  |  |  | 150000
Total Capital Expenditures |  |  |  | 450000
Contingency Fund |  |  |  | 150000
Overall Total Budget |  |  |  | 1800000
Total Projected Revenue |  |  |  | 1250000
Surplus / Deficit |  | Deficit – |  | -550000
Implementation & Timeline
Milestone |  | Description |  | Start Date | End Date
Phase 1: Project Planning |  | Site selection and initial design approval |  | 03/01/20XX | 06/01/20XX
Phase 2: Installation |  | Installation of 50 purification units |  | 07/01/20XX | 03/01/20XX
Phase 3: Training & Monitoring |  | Training staff and system monitoring |  | 04/01/20XX | 12/01/20XX
Approval Workflow
Prepared by |  | Signature |  | Date
Dr. Guadalupe Garcia |  |  |  | February 15, 20XX
Reviewed by |  | Signature |  | Date
Krista Ahmed |  |  |  | February 18, 20XX
Approved by |  | Signature |  | Date
Victoria Pearson |  |  |  | February 22, 20XX
CLICK HERE TO CREATE IN SMARTSHEET
Project Budget Proposal

## BLANK - Budget Proposal
Project Budget Proposal Template
Project Budget Proposal
Project Title
Project Manager
Dr. Guadalupe Garcia
Department / Organization |  |  | Submission Date
Prepared by | Reviewed by |  | Approved by
Project Overview & Objectives
Project Description
Briefly describe the project's purpose, scope, and key deliverables.
Objectives
Objective 1
Objective 2
Objective 3
Budget Summary
Total Budget
0
Expense Breakdown
Personnel Costs | 0
Operating Costs | 0
Capital Expenditures | 0
Contingency Fund | 0
Budget Proposal Justification
Justification
Explain why the requested budget is necessary to achieve the project’s objectives. Provide detailed reasoning for key expenses, including personnel, equipment, or capital investments. Highlight how each budget category contributes to the successful completion of the project and aligns with organizational goals or strategic initiatives.
Key Investments
Personnel
Technology
Training
Anticipated Revenue
Revenue Source |  |  | Amount ($)
Government Grants
Corporate Sponsorships
Donations
Sales Revenue (training materials)
Other (specify)
Total Projected Revenue |  |  | 0
Funding Sources
Funding Source |  |  | Amount ($)
Internal Funding
External Grants / Sponsorships
Other
Total Projected Funding |  |  | 0
Direct Costs
Personnel Costs
Category | Description |  | Amount ($)
Project Manager Salary | Project implementation oversight
Engineers (4) | Technical design and implementation expertise
Local Technicians | System maintenance
Other (specify)
Total Personnel Costs |  |  | 0
Materials & Supplies
Category | Description |  | Amount ($)
Solar Panels & Hardware | Power for purification units
Purification System Materials | Filters, sensors, water storage
Other (specify)
Total Materials & Supplies |  |  | 0
Subcontractors
Category | Description |  | Amount ($)
Installation Contractors | Installation services for 50 units
Training Contractors | On-site training of local staff
Other (specify)
Total Subcontractors |  |  | 0
Total Direct Costs |  |  | 0
Indirect Costs (Overhead)
Category | Description |  | Amount ($)
Overhead Costs | Rent, utilities, and administrative support
Administrative Costs | Legal, finance, and HR services
Other (specify)
Total Indirect Costs |  |  | 0
Capital Expenditures
Category | Description |  | Amount ($)
Equipment Purchases | Solar-powered purification units
Infrastructure Upgrades | Facility expansion for storage
Other (specify)
Total Capital Expenditures |  |  | 0
Contingency & Risk Management
Contingency Fund
0
Justification for Contingency
Explain why a contingency fund is necessary for this project, such as accounting for unexpected costs, delays, or changes in project scope.
Risk Assessment
Risks |  | Mitigation Strategies
Cost Summary
Category |  |  | Total ($)
Total Direct Costs |  |  | 0
Total Indirect Costs |  |  | 0
Total Capital Expenditures |  |  | 0
Contingency Fund |  |  | 0
Overall Total Budget |  |  | 0
Total Projected Revenue |  |  | 0
Surplus / Deficit |  |  | 0
Implementation & Timeline
Milestone | Description |  | Start Date | End Date
Approval Workflow
Prepared by | Signature |  | Date
0
Reviewed by | Signature |  | Date
0
Approved by | Signature |  | Date
0
Project Budget Proposal

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.