## Commercial Tenant Improvement
Commercial Improvement Gantt Template
Client Name | [5 empty] | Project Location
Name | [5 empty] | Address
Project Lead
Name
Start Date | Projected End Date
MM/DD/YY | MM/DD/YY
[6 empty] | Month 1 |  |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  |  | Month 6
Activity | Assigned To (Subcontractor or Team) | Start Date | End Date | Duration (in days) | Percent Complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Phase 1: Preconstruction |  | 2036-03-12 | 2036-03-23 | 12 | bar: Month 1 1 to Month 1 2
Space Planning |  | 2036-03-12 | 2036-03-15 | 4 | 100% | bar: Month 1 1
Landlord Approval |  | 2036-03-15 | 2036-03-16 | 2 | 100% | bar: Month 1 1
Permit Submission |  | 2036-03-15 | 2036-03-21 | 7 | 90% | bar: Month 1 1 to Month 1 2
Permit Issuance |  | 2036-03-16 | 2036-03-22 | 7 | 40% | bar: Month 1 1 to Month 1 2
|  | 2036-03-17 | 2036-03-22 | 6 | 70% | bar: Month 1 1 to Month 1 2
|  | 2036-03-18 | 2036-03-22 | 5 | 60% | bar: Month 1 1 to Month 1 2
|  | 2036-03-23 | 2036-03-23 | 1 | 50% | bar: Month 1 2
Phase 2: Demo and Rough-In |  | 2026-03-24 | 2026-04-02 | 10 | bar: Month 1 3 to Month 1 4
Interior Demo |  | 2026-03-24 | 2026-03-28 | 5 | 5% | bar: Month 1 3
Trash Haul |  | 2026-03-29 | 2026-04-02 | 5 | 30% | bar: Month 1 3 to Month 1 4
Framing |  |  |  |  | 0%
MEP Rough-In |  |  |  |  | 0%
Phase 3: Systems and Infrastructure |  | 0 | 0 | 1
HVAC Install |  |  |  |  | 0%
Fire Protection Install |  |  |  |  | 0%
Electrical Panels |  |  |  |  | 0%
Low-Voltage Cabling |  |  |  |  | 0%
0%
0%
Phase 4: Interior Build Out |  | 0 | 0 | 1
Drywall |  |  |  |  | 0%
Taping and Texture |  |  |  |  | 0%
Painting |  |  |  |  | 0%
Flooring |  |  |  |  | 0%
Phase 5: Fixtures and Finishes |  | 0 | 0 | 1
Lighting Install |  |  |  |  | 0%
Casework |  |  |  |  | 0%
Signage |  |  |  |  | 0%
Final Cleaning |  |  |  |  | 0%
Phase 6: Inspections and Turnover |  | 0 | 0 | 1
Final Inspections |  |  |  |  | 0%
Punch List |  |  |  |  | 0%
Tenant Walk-Through |  |  |  |  | 0%
Certificate of Occupancy |  |  |  |  | 0%
Other |  | 0 | 0 | 1
0%
0%
0%
0%
CLICK HERE TO CREATE IN SMARTSHEET | bar: Month 1 1 to Month 3 15
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.