## Construction Project Gantt
Construction Project Gantt Chart Template
Project Name |  |  |  | Start Date
Name |  |  |  | 2031-10-01
Project Manager |  |  |  | End Date
Name |  |  |  | 2032-06-01
Location
Address
Start and End Dates for the Major Phases auto-populate to match the start date of the first task and the end date of the last task in each phase.
Task Description | Task Owner | Start Date | End Date | Duration in days (auto-populates) | Percent Complete
Phase 1 - Preconstruction and Planning | Name | 2031-10-06 | 2031-11-15 | 41 | 100%
Permits | Name | 2031-10-06 | 2031-10-24 | 19 | 50%
Design Finalized |  | 2031-10-25 | 2031-10-29 | 5 | 10%
Permitting |  | 2031-11-01 | 2031-11-13 | 13 | 100%
Budget Approved |  | 2031-11-13 | 2031-11-15 | 3 | 0%
Phase 2 - Site Preparation and Mobilization |  | 2031-10-29 | 2031-12-20 | 53 | 0%
Site Access Setup |  | 2031-11-19 | 2031-12-10 | 22 | 0%
Utility Coordination |  | 2031-10-29 | 2031-12-09 | 42 | 0%
Equipment Delivery |  | 2031-11-22 | 2031-12-15 | 24 | 0%
Safety Review |  | 2031-11-29 | 2031-12-20 | 22 | 0%
Phase 3 - Framing |  | 2031-12-10 | 2032-01-23 | 45 | 0%
Frame Walls |  | 2031-12-10 | 2031-12-12 | 3 | 0%
Frame Roof |  | 2031-12-17 | 2031-12-25 | 9 | 0%
Sheathing |  | 2031-12-25 | 2031-12-31 | 7 | 0%
Framing Inspection |  | 2031-12-31 | 2032-01-23 | 24 | 0%
Phase 4 - Construction Build Out |  | 2032-01-04 | 2032-03-11 | 68 | 0%
Structural Work |  | 2032-01-04 | 2032-01-13 | 10 | 0%
MEP Installation |  | 2032-02-16 | 2032-03-11 | 25 | 0%
Roofing |  | 2032-01-19 | 2032-03-10 | 52 | 0%
Exterior Finishes |  | 2032-02-03 | 2032-02-14 | 12 | 0%
Phase 5 - Interior Systems |  | 2032-02-15 | 2032-04-14 | 60 | 0%
Insulation |  | 2032-02-16 | 2032-02-23 | 8 | 0%
Drywall |  | 2032-02-25 | 2032-03-09 | 14 | 0%
Systems Install |  | 2032-02-15 | 2032-02-21 | 7 | 0%
Painting |  | 2032-02-28 | 2032-04-14 | 47 | 0%
Phase 7 - Final Inspection and Closeout |  | 2032-05-01 | 2032-06-01 | 32 | 0%
Final Inspections |  | 2032-05-01 | 2032-05-11 | 11 | 0%
Punch List |  | 2032-05-11 | 2032-05-15 | 5 | 0%
Cleaning |  | 2032-05-16 | 2032-05-22 | 7 | 0%
Project Handoff |  | 2032-05-25 | 2032-06-01 | 8 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Start Date = MIN([Start Date, row below]:D17)
End Date = MAX([End Date, row below]:E17)
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.