## EXAMPLE Critical Path
Critical Path Template for Construction Example
Project Title |  | Start
Project Alpha |  | 2025-09-21
Project Manager |  | End
Lori Garcia |  | 2025-12-30 |  | Estimated Completion Date auto-populates. |  |  | Critical Path auto-populates.
WBS ID | Task Name | Estimated Start Date | Estimated Duration in days | Estimated End Date | Predecessors | Float (days) | On Critical Path | Comments
1 | Obtain Permits | 2035-09-21 | 10 | 2035-10-01 |  | 0 | Yes
1.1 | Site Prep | 2035-10-01 | 6 | 2035-10-07 | 1 | 0 | Yes
1.2 | Foundation Work | 2035-10-06 | 18 | 2035-10-24 | 1.1 | 0 | Yes
1.3 | Framing | 2035-10-25 | 4 | 2035-10-29 | 1.2 | 0 | Yes
1.4 | MEP Rough-In | 2035-11-01 | 12 | 2035-11-13 | 1.3 | 2 | No
1.5 | Inspections | 2035-11-13 | 5 | 2035-11-18 | 1.4 | 0 | Yes
1.6 | Finishes | 2035-10-25 | 40 | 2035-12-04 | 1.5 | 3 | No
1.7 | Final Walkthrough | 2035-11-19 | 20 | 2035-12-09 | 1.6 | 0 | Yes
|  | 2035-10-29 | 0 | 2035-10-29 |  |  | Yes
|  | 2035-11-22 | 0 | 2035-11-22 |  |  | Yes
|  | 2035-11-29 | 0 | 2035-11-29 |  |  | Yes
|  | 2035-12-10 | 0 | 2035-12-10 |  |  | Yes
|  | 2035-12-10 | 0 | 2035-12-10 |  |  | Yes
|  | 2035-12-27 | 0 | 2035-12-27 |  |  | Yes
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Estimated End Date = [Estimated Start Date]+[Estimated Duration in days]

## BLANK Critical Path
Critical Path Template for Construction
Project Title |  | Start
Project Manager |  | End
|  |  |  | Estimated Completion Date auto-populates. |  |  | Critical Path auto-populates.
WBS ID | Task Name | Estimated Start Date | Estimated Duration in days | Estimated End Date | Predecessors | Float (days) | On Critical Path | Comments
1 |  | 2035-09-21 | 10 | 2035-10-01 |  | 0 | Yes
1.1 |  | 2035-10-01 | 6 | 2035-10-07 | 1 | 0 | Yes
1.2 |  | 2035-10-06 | 18 | 2035-10-24 | 1.1 | 0 | Yes
1.3 |  | 2035-10-25 | 4 | 2035-10-29 | 1.2 | 0 | Yes
1.4 |  | 2035-11-01 | 12 | 2035-11-13 | 1.3 | 2 | No
1.5 |  | 2035-11-13 | 5 | 2035-11-18 | 1.4 | 0 | Yes
1.6 |  | 2035-10-25 | 40 | 2035-12-04 | 1.5 | 3 | No
1.7 |  | 2035-11-19 | 20 | 2035-12-09 | 1.6 | 0 | Yes
|  | 2035-10-29 | 0 | 2035-10-29 |  |  | Yes
|  | 2035-11-22 | 0 | 2035-11-22 |  |  | Yes
|  | 2035-11-29 | 0 | 2035-11-29 |  |  | Yes
|  | 2035-12-10 | 0 | 2035-12-10 |  |  | Yes
|  | 2035-12-10 | 0 | 2035-12-10 |  |  | Yes
|  | 2035-12-27 | 0 | 2035-12-27 |  |  | Yes
Formulas:
Estimated End Date = [Estimated Start Date]+[Estimated Duration in days]
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.