## HVAC Install Gantt
HVAC Install Gantt Template
Project Name |  |  | Start Date
Name |  |  | 2035-09-01 |  |  | <-- Enter the start date at the top of the template to populate the timeline and auto-fill the shaded start and end dates below.
[6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
Tasks | Assigned To | 0 | Start | End | Days | 2035-09-01 | 2035-09-02 | 2035-09-03 | 2035-09-04 | 2035-09-05 | 2035-09-06 | 2035-09-07 | 2035-09-10 | 2035-09-11 | 2035-09-12 | 2035-09-13 | 2035-09-14 | 2035-09-17 | 2035-09-18 | 2035-09-19 | 2035-09-20 | 2035-09-21 | 2035-09-24 | 2035-09-25 | 2035-09-26 | 2035-09-27 | 2035-09-28 | 2035-10-01 | 2035-10-02 | 2035-10-03 | 2035-10-04 | 2035-10-05 | 2035-10-08 | 2035-10-09 | 2035-10-10
Planning and Prep | Name | 100% | 2035-09-01 | 2035-09-05 | 3 | A | A | A | A | A
Load Calculations | Name | 0% | 2035-09-01 | 2035-09-02 | 0 | A | A
Equipment Selection |  | 0% | 2035-09-02 | 2035-09-02 | 0 |  | A
Duct Layout Finalized |  | 25% | 2035-09-03 | 2035-09-03 | 1 |  |  | A
Permits Submitted |  | 25% | 2035-09-04 | 2035-09-04 | 1 |  |  |  | A
|  | 25% | 2035-09-05 | 2035-09-05 | 1 |  |  |  |  | A
Procurement and Staging |  | 45% | 2035-09-05 | 2035-09-15 | 8 |  |  |  |  | A | A | A | A | A | A | A | A
Order Equipment |  | 10% | 2035-09-05 | 2035-09-05 | 1 |  |  |  |  | A
Receive Materials |  | 5% | 2035-09-05 | 2035-09-05 | 1 |  |  |  |  | A
Site Preparation |  | 55% | 2035-09-08 | 2035-09-12 | 3 | [7 empty] | A | A | A
Pre-Install Walkthrough |  | 89% | 2035-09-11 | 2035-09-15 | 4 | [8 empty] | A | A | A | A
|  | 0% | 2035-09-11 | 2035-09-15 | 4 | [8 empty] | A | A | A | A
Installation - Rough Phase |  | 100% | 2035-09-15 | 2035-09-20 | 4 | [12 empty] | A | A | A | A
Install Ductwork |  | 0% | 2035-09-15 | 2035-09-16 | 0
Set Air Handler / Furnace |  | 5% | 2035-09-17 | 2035-09-17 | 1 | [12 empty] | A
Install Refrigerant Lines |  | 10% | 2035-09-18 | 2035-09-19 | 2 | [13 empty] | A | A
Electrical Rough-In |  | 15% | 2035-09-19 | 2035-09-20 | 2 | [14 empty] | A | A
|  | 15% | 2035-09-15 | 2035-09-17 | 1 | [12 empty] | A
Installation - Final Phase |  | 100% | 2035-09-24 | 2035-10-03 | 8 | [17 empty] | A | A | A | A | A | A | A | A
Set Condenser Unit |  | 0% | 2035-09-24 | 2035-09-25 | 2 | [17 empty] | A | A
Thermostat Wiring |  | 0% | 2035-09-25 | 2035-09-26 | 2 | [18 empty] | A | A
System Charge and Startup |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [18 empty] | A | A | A | A
Final Connections |  | 0% | 2035-09-30 | 2035-10-03 | 3 | [22 empty] | A | A | A
Testing and Inspection |  | 100% | 2035-09-25 | 2035-10-07 | 9 | [18 empty] | A | A | A | A | A | A | A | A | A
Pressure Test |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [18 empty] | A | A | A | A
Commissioning |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [18 empty] | A | A | A | A
Permit Inspection |  | 0% | 2035-09-26 | 2035-09-30 | 3 | [19 empty] | A | A | A
Client Walkthrough |  | 0% | 2035-09-27 | 2035-10-01 | 3 | [20 empty] | A | A | A
|  | 0% | 2035-10-03 | 2035-10-07 | 3 | [24 empty] | A | A | A
Closeout |  | 100% | 2035-10-01 | 2035-10-06 | 5 | [22 empty] | A | A | A | A | A
Punch List |  | 0% | 2035-10-01 | 2035-10-02 | 2 | [22 empty] | A | A
Final Documentation |  | 0% | 2035-10-02 | 2035-10-06 | 4 | [23 empty] | A | A | A | A
Warranty Handoff |  | 0% | 2035-10-02 | 2035-10-06 | 4 | [23 empty] | A | A | A | A
|  | 0% | 2035-10-02 | 2035-10-06 | 4 | [23 empty] | A | A | A | A
|  | 0% | 2035-10-02 | 2035-10-06 | 4 | [23 empty] | A | A | A | A
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE:
00/00/00
Brief Description
MILESTONE:
00/00/00
Brief Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.