## Infrastructure Upgrade Gantt
Infrastructure Upgrade Gantt Template
Client Name | Client Person of Contact (POC) |  |  |  |  | Project Location
Name | Name |  |  |  |  | Address
Project Manager |  | Project Manager Phone
Name |  | 000-000-0000
Start Date | Projected End Date
MM/DD/YY | MM/DD/YY
[6 empty] | Month 1 |  |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  |  | Month 6 |  |  |  |  | Month 7 |  |  |  |  | Month 8 |  |  |  |  | Month 9
[6 empty] | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks |  |  |  |  | Weeks
Activity | Assigned To (Subcontractor or Team) | Start Date | End Date | Duration (in days) | Percent Complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
Planning and Permitting |  | 2036-03-12 | 2036-03-23 | 12 | bar: Weeks 1 to Weeks 2
Site Assessment |  | 2036-03-12 | 2036-03-15 | 4 | 100% | bar: Weeks 1
Environmental Review |  | 2036-03-15 | 2036-03-16 | 2 | 100% | bar: Weeks 1
Design Finalized |  | 2036-03-15 | 2036-03-21 | 7 | 90% | bar: Weeks 1 to Weeks 2
Permits Submitted |  | 2036-03-16 | 2036-03-22 | 7 | 40% | bar: Weeks 1 to Weeks 2
Permits Approved |  | 2036-03-17 | 2036-03-22 | 6 | 70% | bar: Weeks 2
|  | 2036-03-18 | 2036-03-22 | 5 | 60% | bar: Weeks 2
|  | 2036-03-23 | 2036-03-23 | 1 | 50% | bar: Weeks 2
Procurement and Mobilization |  | 2026-03-24 | 2026-04-02 | 10 | bar: Weeks 3 to Weeks 4
Bid Process |  | 2026-03-24 | 2026-03-28 | 5 | 5% | bar: Weeks 3
Vendor Selection |  | 2026-03-29 | 2026-04-02 | 5 | 30% | bar: Weeks 3 to Weeks 4
Material Orders |  |  |  |  | 0%
Site Mobilization |  |  |  |  | 0%
Utility Coordination |  |  |  |  | 0%
Demolition and Site Prep |  | 0 | 0 | 1
Removal of Existing Infrastructure |  |  |  |  | 0%
Traffic Control Setup |  |  |  |  | 0%
Temporary Services in Place |  |  |  |  | 0%
0%
0%
Installation and Upgrade Work |  | 0 | 0 | 1
Trenching or Excavation |  |  |  |  | 0%
System Installation |  |  |  |  | 0%
Structural Improvements |  |  |  |  | 0%
Utility Tie-Ins |  |  |  |  | 0%
Testing and Inspection |  | 0 | 0 | 1
System Testing |  |  |  |  | 0%
Safety Review |  |  |  |  | 0%
Third Party Inspection |  |  |  |  | 0%
Compliance Check |  |  |  |  | 0%
Project Closeout |  | 0 | 0 | 1
Final Restoration |  |  |  |  | 0%
Punch List |  |  |  |  | 0%
As-Built Documentation |  |  |  |  | 0%
Project Acceptance |  |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET | bar: Weeks 1 to Weeks 15
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.