## Landscape Project Gantt
Landscaping Project Gantt Chart Template
Project Name |  |  | Start Date
Name |  |  | 2035-09-02 |  |  | <-- Enter the start date at the top of the template to populate the timeline and auto-fill the shaded start and end dates below.
[6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8
Tasks | Assigned To | 0 | Start | End | Days | 2035-09-02 | 2035-09-03 | 2035-09-04 | 2035-09-05 | 2035-09-06 | 2035-09-07 | 2035-09-10 | 2035-09-11 | 2035-09-12 | 2035-09-13 | 2035-09-14 | 2035-09-17 | 2035-09-18 | 2035-09-19 | 2035-09-20 | 2035-09-21 | 2035-09-24 | 2035-09-25 | 2035-09-26 | 2035-09-27 | 2035-09-28 | 2035-10-01 | 2035-10-02 | 2035-10-03 | 2035-10-04 | 2035-10-05 | 2035-10-08 | 2035-10-09 | 2035-10-10 | 2035-10-11 | 2035-10-12 | 2035-10-15 | 2035-10-16 | 2035-10-17 | 2035-10-18 | 2035-10-19 | 2035-10-22 | 2035-10-23 | 2035-10-24 | 2035-10-25
Planning and Design | Name | 100% | 2035-09-02 | 2035-09-05 | 3 | A | A | A | A
Site Assessment | Name | 0% | 2035-09-02 | 2035-09-02 | 0 | A
Budget Estimation |  | 0% | 2035-09-02 | 2035-09-02 | 0 | A
Initial Design |  | 25% | 2035-09-03 | 2035-09-03 | 1 |  | A
Revise & Finalize Design |  | 25% | 2035-09-04 | 2035-09-04 | 1 |  |  | A
Permits & Approvals |  | 25% | 2035-09-05 | 2035-09-05 | 1 |  |  |  | A
Site Preparation |  | 45% | 2035-09-05 | 2035-09-15 | 8 |  |  |  | A | A | A | A | A | A | A | A
Site Clearing |  | 10% | 2035-09-05 | 2035-09-05 | 1 |  |  |  | A
Excavation |  | 5% | 2035-09-05 | 2035-09-05 | 1 |  |  |  | A
Soil Prep |  | 55% | 2035-09-08 | 2035-09-12 | 3 | [6 empty] | A | A | A
Grading |  | 89% | 2035-09-11 | 2035-09-15 | 4 | [7 empty] | A | A | A | A
Hardscape Installation |  | 100% | 2035-09-15 | 2035-09-20 | 4 | [11 empty] | A | A | A | A
Foundation |  | 0% | 2035-09-15 | 2035-09-16 | 0
Retaining Walls |  | 5% | 2035-09-17 | 2035-09-17 | 1 | [11 empty] | A
Patios |  | 10% | 2035-09-18 | 2035-09-19 | 2 | [12 empty] | A | A
Pathways |  | 15% | 2035-09-19 | 2035-09-20 | 2 | [13 empty] | A | A
Outdoor Structures |  | 15% | 2035-09-15 | 2035-09-17 | 1 | [11 empty] | A
Drainage |  | 35% | 2035-09-17 | 2035-09-18 | 2 | [11 empty] | A | A
Irrigation System |  | 0% | 2035-09-18 | 2035-09-19 | 2 | [12 empty] | A | A
Softscaping |  | 100% | 2035-09-24 | 2035-10-03 | 8 | [16 empty] | A | A | A | A | A | A | A | A
Trees & Shrubs |  | 0% | 2035-09-24 | 2035-09-25 | 2 | [16 empty] | A | A
Flower Beds & Ground Cover |  | 0% | 2035-09-25 | 2035-09-26 | 2 | [17 empty] | A | A
Seeding & Sodding |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [17 empty] | A | A | A | A
Mulching |  | 0% | 2035-09-30 | 2035-10-03 | 3 | [21 empty] | A | A | A
Lighting & Electrical |  | 100% | 2035-09-25 | 2035-09-29 | 4 | [17 empty] | A | A | A | A
Wiring & Setup |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [17 empty] | A | A | A | A
Installation |  | 0% | 2035-09-25 | 2035-09-29 | 4 | [17 empty] | A | A | A | A
Water Features |  | 100% | 2035-10-03 | 2035-10-08 | 4 | [23 empty] | A | A | A | A
Pond & Fountain Installation |  | 0% | 2035-10-03 | 2035-10-07 | 3 | [23 empty] | A | A | A
Water Pump & Filtration System |  | 0% | 2035-10-03 | 2035-10-07 | 3 | [23 empty] | A | A | A
Stones & Foliage |  | 0% | 2035-10-07 | 2035-10-08 | 1 | [26 empty] | A
Final Touches |  | 100% | 2025-10-10 | 2035-10-06 | 2606 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Lawn Care |  | 0% | 2035-10-01 | 2035-10-02 | 2 | [21 empty] | A | A
Stone & Gravel |  | 0% | 2035-10-02 | 2035-10-06 | 4 | [22 empty] | A | A | A | A
Clean-Up |  | 0% | 2025-10-10 | 2025-10-14 | 3
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE:
00/00/00
Brief Description
MILESTONE:
00/00/00
Brief Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.