## Residential Build Gantt
Residential Build Gantt Template
Client Name |  |  |  | Start Date
Name |  |  |  | 2031-10-01
Project Manager |  |  |  | End Date
Name |  |  |  | 2032-06-01
Project Location
Address
Start and End Dates for the Major Phases auto-populate to match the start date of the first task and the end date of the last task in each phase.
Task Description | Task Owner | Start Date | End Date | Duration in days (auto-populates) | Percent Complete
Phase 1 - Preconstruction | Name | 2031-10-06 | 2031-11-15 | 41 | 100%
Site Survey | Name | 2031-10-06 | 2031-10-24 | 19 | 50%
Design Finalized |  | 2031-10-25 | 2031-10-29 | 5 | 10%
Permit Submitted |  | 2031-11-01 | 2031-11-13 | 13 | 100%
Permit Approved |  | 2031-11-13 | 2031-11-15 | 3 | 0%
Phase 2 - Sitework and Foundation |  | 2031-11-19 | 2031-12-20 | 32 | 0%
Excavation |  | 2031-11-19 | 2031-12-10 | 22 | 0%
Form Footings |  | 2031-10-29 | 2031-12-09 | 42 | 0%
Pour Foundation |  | 2031-11-22 | 2031-12-15 | 24 | 0%
Foundation Inspection |  | 2031-11-29 | 2031-12-20 | 22 | 0%
Phase 3 - Framing |  | 2031-12-10 | 2032-01-23 | 45 | 0%
Frame Walls |  | 2031-12-10 | 2031-12-12 | 3 | 0%
Frame Roof |  | 2031-12-17 | 2031-12-25 | 9 | 0%
Sheathing |  | 2031-12-25 | 2031-12-31 | 7 | 0%
Framing Inspection |  | 2031-12-31 | 2032-01-23 | 24 | 0%
Phase 4 - Exterior Work |  | 2032-01-04 | 2032-02-14 | 42 | 0%
Install Windows |  | 2032-01-04 | 2032-01-13 | 10 | 0%
Siding |  | 2032-02-16 | 2032-03-11 | 25 | 0%
Roofing |  | 2032-01-19 | 2032-03-10 | 52 | 0%
Exterior Doors |  | 2032-02-03 | 2032-02-14 | 12 | 0%
Phase 5 - Interior Systems |  | 2032-02-16 | 2032-04-14 | 59 | 0%
Rough Plumbing |  | 2032-02-16 | 2032-02-23 | 8 | 0%
Electrical Wiring |  | 2032-02-25 | 2032-03-09 | 14 | 0%
HVAC Rough-In |  | 2032-02-15 | 2032-02-21 | 7 | 0%
Systems Inspection |  | 2032-02-28 | 2032-04-14 | 47 | 0%
Phase 6 - Interior Finishes |  | 2032-02-28 | 2032-05-03 | 66 | 0%
Insulation |  | 2032-02-28 | 2032-03-10 | 12 | 0%
Drywall |  | 2032-02-28 | 2032-03-22 | 24 | 0%
Flooring |  | 2032-04-03 | 2032-04-13 | 11 | 0%
Paint |  | 2032-04-12 | 2032-05-03 | 22 | 0%
Phase 7 - Final Inspection and Closeout |  | 2032-05-03 | 2032-06-01 | 30 | 0%
Final Walkthrough |  | 2032-05-03 | 2032-05-11 | 9 | 0%
Punch List |  | 2032-05-11 | 2032-05-15 | 5 | 0%
Final Inspection |  | 2032-05-16 | 2032-05-22 | 7 | 0%
Certificate of Occupancy |  | 2032-05-25 | 2032-06-01 | 8 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Start Date = [Start Date, row below]
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.