## Residential Remodel Gantt
Residential Remodel Gantt Template
Client Name | [5 empty] | Project Location
Name | [5 empty] | Address
Project Lead
Name
Start Date | Projected End Date
MM/DD/YY | MM/DD/YY
[6 empty] | Month 1 |  |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  |  | Month 6
Activity | Assigned To | Start Date | End Date | Duration (in days) | Percent Complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Phase 1: Preconstruction |  | 2026-03-12 | 2026-03-23 | 12 | bar: Month 1 1 to Month 1 2
Initial Walkthrough |  | 2026-03-12 | 2026-03-15 | 4 | 100% | bar: Month 1 1
Scope Finalized |  | 2026-03-15 | 2026-03-16 | 2 | 100% | bar: Month 1 1
Permit Submitted |  | 2026-03-15 | 2026-03-21 | 7 | 90% | bar: Month 1 1 to Month 1 2
Materials Ordered |  | 2026-03-16 | 2026-03-22 | 7 | 40% | bar: Month 1 1 to Month 1 2
|  | 2026-03-17 | 2026-03-22 | 6 | 70% | bar: Month 1 1 to Month 1 2
|  | 2026-03-18 | 2026-03-22 | 5 | 60% | bar: Month 1 1 to Month 1 2
|  | 2026-03-23 | 2026-03-23 | 1 | 50% | bar: Month 1 1 to Month 1 2
Phase 2: Demo and Prep |  | 2026-03-24 | 2026-04-02 | 10 | bar: Month 1 3 to Month 1 4
Clear Work Area |  | 2026-03-24 | 2026-03-28 | 5 | 5% | bar: Month 1 3
Protect Finishes |  | 2026-03-29 | 2026-04-02 | 5 | 30% | bar: Month 1 3 to Month 1 4
Demolition |  |  |  |  | 0%
Site Cleanup |  |  |  |  | 0%
Phase 3: Structural and Rough Work |  | 0 | 0 | 1
Wall Framing |  |  |  |  | 0%
Plumbing Rough-In |  |  |  |  | 0%
Electrical Rough-In |  |  |  |  | 0%
Inspection |  |  |  |  | 0%
0%
0%
Phase 4: Mechanical / Systems Upgrades |  | 0 | 0 | 1
HVAC Install |  |  |  |  | 0%
Venting |  |  |  |  | 0%
Low-Voltage Wiring |  |  |  |  | 0%
0%
Phase 5: Interior Finishes |  | 0 | 0 | 1
Drywall |  |  |  |  | 0%
Painting |  |  |  |  | 0%
Flooring |  |  |  |  | 0%
Tile Work |  |  |  |  | 0%
Phase 6: Fixture and Trim Installation |  | 0 | 0 | 1
Coutertops, Lighting, Molding, Trim |  |  |  |  | 0%
Paint Touchups |  |  |  |  | 0%
Plumbing Fixtures
Phase 7: Final Inspection and Punch List |  | 0 | 0 | 1
Final Walkthrough
Punch List Items
Final Inspection
Client Sign-Off
CLICK HERE TO CREATE IN SMARTSHEET | bar: Month 1 1 to Month 3 15
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.