## EXAMPLE Virtual Event Planning
Virtual Event Planning Gantt Chart Template Example
EVENT |  |  |  | PLANNING START DATE | PLANNING END DATE
Virtual Conference |  |  |  | MM/DD/YY | MM/DD/YY
PROJECT MANAGER |  |  |  | DATE OF EVENT
Brody B. |  |  |  | MM/DD/YY
| TIMELINE |  |  | PROJECT NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Establish virtual event goals | 2025-05-05 | 2025-07-01 | 58 |  | 0
Develop event theme and title | 2025-05-10 | 2025-08-10 | 93 |  | 0
Choose event platform | 2025-06-10 | 2026-03-01 | 265 |  | 0
Create event budget | 2025-06-22 | 2025-08-04 | 44 |  | 0
Create content/speaker and wish list | 2025-07-14 | 2025-11-01 | 111 |  | 0
Create sponsor wish list | 2025-07-14 | 2026-01-20 | 191
Identify team roles | 2025-08-01 | 2025-10-01 | 62
Define target audience | 2025-08-14 | 2025-08-30 | 17
Determine AV/production and tech needs | 2025-09-01 | 2025-12-10 | 101
Confirm speaker and moderator | 2025-10-01 | 2025-11-15 | 46
Develop attendee engagement strategy | 2025-10-01 | 2025-12-01 | 62
Test run sound and AV equipment | 2025-11-01 | 2025-12-01 | 31
Communicate event functions to registrants | 2025-11-10 | 2025-12-10 | 31
Test attendee engagement tools and features | 2025-12-01 | 2026-02-10 | 72
DELIVERY TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Virtual Event Planning
Virtual Event Planning Gantt Chart Template
EVENT |  |  |  | PLANNING START DATE | PLANNING END DATE
Name |  |  |  | MM/DD/YY | MM/DD/YY
PROJECT MANAGER |  |  |  | DATE OF EVENT
Name |  |  |  | MM/DD/YY
| TIMELINE |  |  | PROJECT NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
1
1
1
1
1
1
1
1
1
DELIVERY TIMELINE
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.