{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["New Home Construction Timeline"],"not_rendered":{"charts":1,"images":1,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"New Home Construction Timeline","index":0,"n_rows":60,"n_cols":26,"rows_kept":60,"cut":false,"hidden":false,"merged":[[59,2,59,23],[59,25,59,46]]}
[null,"NEW HOME CONSTRUCTION TIMELINE TEMPLATE"]
[]
[null,"WBS","TASK NAME","START DATE","END DATE","DURATION IN DAYS"]
[null,1,"PRE-CONSTRUCTION","2016-09-15","2016-10-14",{"$f":"E4-D4","v":29}]
[null,1.1000000000000001,"Contracts","2017-10-06","2017-10-24",18]
[null,1.2,"Financing","2017-10-25","2017-10-29",4]
[null,2,"FOUNDATION","2017-11-01","2017-11-13",{"$f":"E7-D7","v":12}]
[null,2.1,"Layout, Pour, and Pin Footings","2017-11-13","2017-11-15",{"$f":"E8-D8","v":2}]
[null,2.2000000000000002,"Block, Mortar, Sand Foundation","2017-10-25","2017-12-05",41]
[null,3,"DRAW #1","2017-11-19","2017-12-10",21]
[null,3.1,"Steel and Lumber Delivery","2017-10-29","2017-12-09",41]
[null,3.2,"Waterproofing and Drain Tile","2017-11-22","2017-12-15",23]
[null,4,"FRAMING","2017-11-29","2017-12-20",21]
[null,4.0999999999999996,"Set Steel","2017-12-10","2017-12-22",12]
[null,4.2,"Deck Framing","2017-12-10","2017-12-15",5]
[null,4.3,"Specialty Rough-Ins (Alarm, Cable, etc.)","2017-12-10","2017-12-15",{"$f":"E16-D16","v":5}]
[null,5,"ROOF","2017-12-27","2017-12-30",3]
[null,5.0999999999999996,"Roof Trusses","2017-12-03","2017-12-21",18]
[null,5.2,"Roofing Paper and Shingles","2018-01-03","2018-01-23",20]
[null,6,"DRAW #2","2018-01-03","2018-01-17",14]
[null,6.1,"Wall Framing","2018-01-04","2018-01-13",9]
[null,6.2,"Windows and Doors","2018-02-16","2018-03-11",23]
[null,7,"EXTERIOR FINISHES","2018-01-19","2018-03-10",50]
[null,7.1,"Siding","2018-02-03","2018-02-14",11]
[null,7.2,"Trim and Brick Veneer","2018-01-18","2018-03-06",47]
[null,8,"PLUMBING/ELECTRICAL/HVAC","2018-02-16","2018-02-23",7]
[null,8.1,"Plumbing/Electrical/HVAC Rough-In","2018-02-25","2018-03-09",12]
[null,8.1999999999999993,"Inspections","2018-02-15","2018-02-17",2]
[null,9,"DRAW #3","2018-02-28","2018-04-14",45]
[null,9.1,"Frame Basement","2018-03-21","2018-03-31",10]
[null,9.1999999999999993,"Frame Bulkheads","2018-02-28","2018-03-10",10]
[null,10,"INSULATION/DRYWALL","2018-02-28","2018-03-18",18]
[null,10.1,"Caulk, Air Seal, Draft and Fire Stop, Insulation","2018-05-03","2018-05-13",10]
[null,10.199999999999999,"Hang, Tape, Finish, and Sand Drywall","2018-05-02","2018-05-03",1]
[null,11,"INTERIOR FINISHES","2018-05-02","2018-05-05",3]
[null,11.1,"Interior Walls and Trim","2018-05-03","2018-05-11",8]
[null,11.2,"Cabinetry and Countertops","2018-05-09","2018-05-13",4]
[null,12,"DRAW #4","2018-05-13","2018-05-18",5]
[null,12.1,"Paint Cabinets and Doors","2018-05-02","2018-05-02",0]
[null,12.2,"Switch and Plug Finishing","2018-05-09","2018-06-05",27]
[null,13,"FLOORING","2018-05-29","2018-06-10",12]
[null,13.1,"Tile and Hardwood Install, Sand, Stain, Seal","2018-05-30","2018-06-10",11]
[null,13.2,"Carpet Install","2018-05-31","2018-06-03",3]
[null,14,"FIXTURES AND APPLIANCES","2018-06-01","2018-06-04",3]
[null,14.1,"Remaining Lights/Fans","2018-06-02","2018-06-05",3]
[null,14.2,"Appliance Install","2018-06-03","2018-06-06",3]
[null,15,"DRAW #5","2018-06-04","2018-06-07",3]
[null,15.1,"Door Hardware","2018-06-05","2018-06-08",3]
[null,15.2,"Bath Hardware","2018-06-06","2018-06-09",3]
[null,16,"LANDSCAPING/DESIGN","2018-06-07","2018-06-10",3]
[null,16.100000000000001,"Patios, Porches, Decks, Drive and Walkways","2018-06-08","2018-06-11",3]
[null,16.2,"Yard, Plants, Groundskeeping","2018-06-09","2018-06-12",3]
[null,17,"FINAL DETAILS/CLOSEOUT","2018-06-10","2018-06-13",3]
[null,17.100000000000001,"Final Walk-Through","2018-06-11","2018-06-14",3]
[null,17.2,"Final Touch-Ups","2018-06-12","2018-06-15",3]
[null,18,"FINAL DRAW","2018-06-13","2018-06-16",3]
[null,18.100000000000001,"Cleaning ","2018-06-14","2018-06-17",3]
[null,18.2,"Move-In","2018-06-15","2018-06-18",3]
[]
[null,null,"CLICK HERE TO CREATE A NEW HOME CONSTRUCTION TIMELINE TEMPLATE IN SMARTSHEET",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"CLICK HERE TO CREATE NEW HOME CONSTRUCTION TIMELINE TEMPLATES IN SMARTSHEET"]