## Program Management Dashboard
PROGRAM MANAGEMENT DASHBOARD
TASK TIMELINE
| PENDING TASKS | RISKS |  |  | ISSUES |  |  | BUDGET | % COMPLETE
| 10 | LOW | 48 |  | OPEN | 18 |  | 88% | 28.57%
|  | MEDIUM | 44 |  | REVISIONS | 16
|  | HIGH | 52 |  | PENDING | 27
TASK TIMELINE
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
| TASK | OWNER | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
| Kick-off | Anna
| Set Objectives | Ken
| Project Requirements | Sara
| Hardware Requirements | James
| Finalize Resource Plan | Anna
| Investor Presentation | Ken
| Staffing | Sara
| Construction | James
| Alpha Out | Pete
| Alpha Testing | Jason
| Beta Out | Pete
| Beta Testing | Jason
| Launch | Pete
| Future Planning | Anna
CLICK HERE TO CREATE PROGRAM MANAGEMENT DASHBOARD TEMPLATES IN SMARTSHEET

## Program Data
PROGRAM MANAGEMENT DATA
TASK TABLE & TIMELINE | [6 empty] | TASK STATUS TRACKING
TASK | OWNER | BEGIN | FINISH | # of DAYS | STATUS |  | STATUS | AMOUNT | %
Kick-off | Anna | 2016-05-05 | 2016-05-06 | 1 | COMPLETE |  | COMPLETE | 4 | 28.57%
Set Objectives | Ken | 2016-05-07 | 2016-05-12 | 5 | COMPLETE |  | OVERDUE | 2 | 14.29%
Project Requirements | Sara | 2016-05-13 | 2016-05-20 | 7 | COMPLETE |  | IN PROGRESS | 2 | 14.29%
Hardware Requirements | James | 2016-05-17 | 2016-05-22 | 5 | COMPLETE |  | NOT STARTED | 6 | 42.86%
Finalize Resource Plan | Anna | 2016-05-23 | 2016-05-27 | 4 | OVERDUE
Investor Presentation | Ken | 2016-06-04 | 2016-06-05 | 1 | OVERDUE
Staffing | Sara | 2016-06-01 | 2016-06-05 | 4 | IN PROGRESS |  | BUDGET
Construction | James | 2016-06-06 | 2016-06-27 | 21 | IN PROGRESS
Alpha Out | Pete | 2016-06-28 | 2016-06-29 | 1 | NOT STARTED |  | PROJECTED | ACTUAL | REMAINDER
Alpha Testing | Jason | 2016-06-29 | 2016-07-15 | 16 | NOT STARTED |  | 1000000 | 880000 | 120000
Beta Out | Pete | 2016-07-16 | 2016-07-17 | 1 | NOT STARTED
Beta Testing | Jason | 2016-07-17 | 2016-07-30 | 13 | NOT STARTED
Launch | Pete | 2016-08-01 | 2016-08-02 | 1 | NOT STARTED
Future Planning | Anna | 2016-08-02 | 2016-08-04 | 2 | NOT STARTED
RISKS & PENDING ACTIONS
TASK | RISKS |  |  | OPEN |  | PENDING ACTIONS
| HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Kick-off | 1 | 0 | 4 | 2 | 0 | 4
Set Objectives | 2 | 3 | 5 | 1 | 2 | 3
Project Requirements | 3 | 4 | 3 | 2 | 1 | 2
Hardware Requirements | 5 | 8 | 1 | 1 | 0 | 0
Finalize Resource Plan | 8 | 6 | 4 | 0 | 3 | 1
Investor Presentation | 5 | 0 | 0 | 2 | 0 | 2
Staffing | 6 | 4 | 0 | 1 | 2 | 3
Construction | 7 | 3 | 3 | 0 | 1 | 4
Alpha Out | 0 | 2 | 4 | 1 | 3 | 2
Alpha Testing | 4 | 4 | 5 | 2 | 0 | 0
Beta Out | 3 | 6 | 4 | 3 | 2 | 0
Beta Testing | 2 | 3 | 6 | 0 | 1 | 1
Launch | 1 | 1 | 7 | 1 | 0 | 2
Future Planning | 5 | 0 | 2 | 2 | 1 | 3
| 52 | 44 | 48 | 18 | 16 | 27
CLICK HERE TO CREATE PROGRAM MANAGEMENT DASHBOARD TEMPLATES IN SMARTSHEET