## Project Management Dashboard
PROJECT MANAGEMENT DASHBOARD
PROJECT NAME | [Name]
REPORT DATE | [Date]
PROJECT STATUS | On track
COMPLETED | 27%
TASKS | ASSIGNED TO | PRIORITY | STATUS
Set Kick-Off Meeting | Alex B. |  | COMPLETE
Agree on Objectives | Frank C. | ★ | COMPLETE
Detailed Requests | Jacob S. |  | COMPLETE
Hardware Requests | Jacob S. | ★ | OVERDUE
Final Resource Plan | Jacob S. |  | IN PROGRESS
Staffing | Alex B. | ★ | IN PROGRESS
Technical Requests | Frank C. |  | NOT STARTED
Testing | Kennedy K. | ★ | NOT STARTED
Dev. Complete | Jacob S. | ★ | NOT STARTED
Hardware Configuration | Alex B. |  | NOT STARTED
System Testing | Kennedy K. | ★ | NOT STARTED
Launch
CLICK HERE TO CREATE IN SMARTSHEET

## Notes
Task Table
Tasks | Assigned To | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2022-09-02 | 2022-09-03 | 1 | COMPLETE
Agree on objectives | Frank C. | 2022-09-03 | 2022-09-07 | 4 | COMPLETE
Detailed Reqs. | Jacob S. | 2022-09-07 | 2022-09-12 | 5 | COMPLETE
Hardward Reqs. | Jacob S. | 2022-09-09 | 2022-09-11 | 2 | OVERDUE
Final Resource Plan | Jacob S. | 2022-09-11 | 2022-09-15 | 4 | IN PROGRESS
Staffing | Alex B. | 2022-09-16 | 2022-09-17 | 1 | IN PROGRESS
Techincal Reqs. | Frank C. | 2022-09-17 | 2022-09-21 | 4 | NOT STARTED
Testing | Kennedy K. | 2022-09-24 | 2022-10-02 | 8 | NOT STARTED
Dev. Complete | Jacob S. | 2022-10-02 | 2022-10-05 | 3 | NOT STARTED
Hardware Config. | Alex B. | 2022-10-05 | 2022-10-07 | 2 | NOT STARTED
System Testing | Kennedy K. | 2022-10-06 | 2022-10-09 | 3 | NOT STARTED
Launch |  | 2022-10-09 | 2022-10-10 | 1
Percentage of Tasks Complete
Complete | 27.27%
Overdue | 9.091%
In progress | 18.18%
Not Started | 45.45%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.