## Transition Plan with Calculator
TRANSITION PLANNING TEMPLATE WITH CALCULATOR
PLAN COMPONENT | TASK / ACTIVITY | PERSON / TEAM RESPONSIBLE | STATUS | NUMBER OF HOURS REQUIRED | START DATE | END DATE | COMMENTS
KEY RELATIONSHIPS | Key relationships outlined | Direct Supervisor | COMPLETED | 1 | 2022-10-20 | 2022-10-21
KEY RELATIONSHIPS | Meeting to discuss vital contacts | Full Department | NOT STARTED | 1.5 | 2022-10-22 | 2022-10-22
KEY RELATIONSHIPS | Create master list of vital contacts | Team Lead | HOLD | 3 | 2022-10-23 | 2022-10-25
KEY RELATIONSHIPS | Announce transition | Human Resources | NOT STARTED | 0.5 | 2022-10-26 | 2022-10-26
KEY RELATIONSHIPS | Provide formal introductions | Direct Supervisor | NOT STARTED | 5 | 2022-10-26 | 2022-10-30
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 11 | 2022-10-20 | 2022-10-30
ASSIGNMENTS | Policy manual compiled and issued | Human Resources | COMPLETED | 0.25 | 2022-10-26 | 2022-10-26
ASSIGNMENTS | On the job training scheduled | Direct Supervisor | COMPLETED | 0.25 | 2022-10-20 | 2022-10-20
ASSIGNMENTS | Senior staff mentor assigned | Direct Supervisor | COMPLETED | 0.5 | 2022-10-20 | 2022-10-20
ASSIGNMENTS | Facility tour scheduled | HR + DS | COMPLETED | 0.25 | 2022-10-20 | 2022-10-24
ASSIGNMENTS | Facility tour conducted | Facilities Manager | COMPLETED | 2 | 2022-10-26 | 2022-10-26
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 3.25 | 2022-10-20 | 2022-10-26
TRAINING | Provide training overview | Direct Supervisor | NOT STARTED | 0.25 | 2022-10-27 | 2022-10-27
TRAINING | Review materials and handouts | Direct Supervisor | NOT STARTED | 1 | 2022-10-27 | 2022-10-27
TRAINING | Discuss training timeline | Direct Supervisor | NOT STARTED | 0.25 | 2022-10-27 | 2022-10-27
TRAINING | Training phase 1 | Trainer | NOT STARTED | 20 | 2022-10-28 | 2022-10-31
TRAINING | Training phase 2 | Trainer | NOT STARTED | 16 | 2022-10-31 | 2022-11-04
TRAINING | Training phase 3 | Trainer | NOT STARTED | 12 | 2022-11-06 | 2022-11-07
TRAINING | Training assessment and review | Direct Supervisor + Trainer | NOT STARTED | 4 | 2022-11-08 | 2022-11-08
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 53.5 | 2022-10-27 | 2022-11-08
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
MEETINGS | Team introduction meeting |  | NOT STARTED | 0.25
MEETINGS | Week 1 review meeting |  | NOT STARTED | 0.25
MEETINGS | Week 2 review meeting |  | NOT STARTED | 0.25
MEETINGS | Week 3 review meeting |  | NOT STARTED | 0.25
MEETINGS | Month 1 review meeting |  | NOT STARTED | 0.5
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 1.5
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
|  |  | OVERALL TRANSITION TOTALS | NUMBER OF HOURS REQUIRED | START DATE | END DATE | TOTAL NUMBER OF DAYS REQUIRED BASED UPON 8.0 HOUR WORK DAY
|  |  |  | 69.25 | 2022-10-20 | 2022-11-08 | 8.6562
CLICK HERE TO CREATE IN SMARTSHEET

## Transition Plan - BLANK
TRANSITION PLANNING TEMPLATE WITH CALCULATOR
PLAN COMPONENT | TASK / ACTIVITIY | PERSON / TEAM RESPONSIBLE | STATUS | NUMBER OF HOURS REQUIRED | START DATE | END DATE | COMMENTS
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
KEY RELATIONSHIPS |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
ASSIGNMENTS |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
TRAINING |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
DELIVERABLES |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
MEETINGS |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
ISSUES + RISKS |  |  |  | 0
| PERSON RESPONSIBLE FOR KNOWLEDGE TRANSFER |  |  | TOTAL HRS | START DATE | END DATE
| RECIPIENT OF KNOWLEDGE TRANSFER |  |  | 0
|  |  | OVERALL TRANSITION TOTALS | NUMBER OF HOURS REQUIRED | START DATE | END DATE | TOTAL NUMBER OF DAYS REQUIRED BASED UPON 8.0 HOUR WORK DAY
|  |  |  | 0 |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.